# Critical Path Analysis with PERT

## Question

A project consists of the following activities with PERT estimates:

| Activity | Predecessor(s) | Optimistic (O) | Most Likely (M) | Pessimistic (P) |
| --- | --- | --- | --- | --- |
| A | — | 3 | 4 | 5 |
| B | — | 2 | 3 | 4 |
| C | — | 4 | 5 | 8 |
| D | A | 5 | 6 | 9 |
| E | A | 3 | 4 | 6 |
| F | B | 6 | 7 | 8 |
| G | C | 2 | 3 | 4 |
| H | D, F | 4 | 5 | 7 |
| I | E, G | 5 | 6 | 9 |
| J | H | 3 | 4 | 6 |
| K | I | 2 | 3 | 4 |
| L | J, K | 3 | 4 | 5 |
| M | L | 1 | 2 | 3 |

## Step 1: TE Calculation

TE = (O + 4M + P) / 6

## Step 2: Forward and Backward Pass with Float

| Activity | TE | ES | EF | LS | LF | Float |
| --- | --- | --- | --- | --- | --- | --- |
| A | 4.00 | 0.00 | 4.00 | 0.00 | 4.00 | 0.00 |
| B | 3.00 | 0.00 | 3.00 | 3.00 | 6.00 | 3.00 |
| C | 5.33 | 0.00 | 5.33 | 5.33 | 10.66 | 5.33 |
| D | 6.33 | 4.00 | 10.33 | 4.00 | 10.33 | 0.00 |
| E | 4.17 | 4.00 | 8.17 | 8.17 | 12.34 | 4.17 |
| F | 7.00 | 3.00 | 10.00 | 10.00 | 17.00 | 7.00 |
| G | 3.00 | 5.33 | 8.33 | 8.33 | 11.33 | 3.00 |
| H | 5.17 | 10.33 | 15.50 | 10.33 | 15.50 | 0.00 |
| I | 6.33 | 8.33 | 14.66 | 14.66 | 21.00 | 6.33 |
| J | 4.17 | 15.50 | 19.67 | 15.50 | 19.67 | 0.00 |
| K | 3.00 | 14.66 | 17.66 | 17.66 | 20.66 | 3.00 |
| L | 4.00 | 19.67 | 23.67 | 19.67 | 23.67 | 0.00 |
| M | 2.00 | 23.67 | 25.67 | 23.67 | 25.67 | 0.00 |

## Step 3: Critical Path using Float (Drift)

Activities with Float = 0 are critical.
Critical Path: A → D → H → J → L → M
Expected Project Duration: ≈ 25.67 days

## Network Diagram

## Step-by-Step Example: Calculating ES, EF, LS, LF for Activity D

Forward Pass for Activity D:
1. Identify predecessors of D: A
2. ES(D) = EF of A = 4.00
3. TE(D) = 6.33 (calculated using PERT formula)
4. EF(D) = ES(D) + TE(D) = 4.00 + 6.33 = 10.33

Backward Pass for Activity D:
1. Identify successors of D: H
2. LF(D) = LS of H = 10.33
3. LS(D) = LF(D) - TE(D) = 10.33 - 6.33 = 4.00

Float Calculation:
Float(D) = LS(D) - ES(D) = 4.00 - 4.00 = 0 (Critical Activity)