### Real-Time Scenario: "Coronary Artery Disease (CAD) Detection System"

Project Goal: Develop a real-time machine learning system that analyzes Cardiac MRI and CT Angiography images to detect blockages in coronary arteries and assess the risk of a heart attack. The system will provide a "Risk Score" to radiologists to aid in diagnosis.

### Risk Identification & Analysis (Qualitative and Quantitative)

Here are the risks associated with this project, categorized according to the lecture.

#### 1. Technology Risks

- Risk ID: T-1

- Risk Description: Model performs poorly on data from a new hospital scanner (different manufacturer, model, or imaging protocol).

- Type: Threat

- Qualitative Analysis:

    - Probability: High (Medical imaging data is notoriously heterogeneous).

    - Impact: High (Misdiagnosis leads to patient harm and legal liability).

    - Exposure: High

- Quantitative Analysis (EMV):

    - Probability: 70%

    - Impact: A lawsuit and reputational damage could cost $5,000,000. Mitigation costs (re-training, data collection) could be $200,000. Total impact: $5,200,000.

    - Risk Exposure (EMV): 0.70 * $5,200,000 = $3,640,000

#### 2. People Risks

- Risk ID: P-1

- Risk Description: The lead AI researcher, who designed the core model architecture, leaves the company.

- Type: Threat

- Qualitative Analysis:

    - Probability: Medium (High demand for AI talent).

    - Impact: High (Project delays, knowledge loss).

    - Exposure: High

- Quantitative Analysis (EMV):

    - Probability: 40%

    - Impact: Recruitment (3 months), project delay (4 months), and ramp-up time. Estimated cost: $400,000.

    - Risk Exposure (EMV): 0.40 * $400,000 = $160,000

#### 3. Organizational Risks

- Risk ID: O-1

- Risk Description: Hospital partners are slow or unwilling to share sufficient annotated data due to privacy concerns (HIPAA/GDPR) and bureaucratic hurdles.

- Type: Threat

- Qualitative Analysis:

    - Probability: High

    - Impact: High (Without data, the model cannot be trained or validated).

    - Exposure: High

- Quantitative Analysis (EMV):

    - Probability: 80%

    - Impact: Project delays and costs for legal frameworks and data anonymization tools: $300,000.

    - Risk Exposure (EMV): 0.80 * $300,000 = $240,000

#### 4. Requirement Risks

- Risk ID: R-1

- Risk Description: Regulatory bodies (like the FDA) introduce new, stringent validation requirements for AI-based medical devices mid-project.

- Type: Threat

- Qualitative Analysis:

    - Probability: Medium

    - Impact: Very High (Requires complete re-testing and documentation, delaying launch).

    - Exposure: High

- Quantitative Analysis (EMV):

    - Probability: 50%

    - Impact: Additional clinical trials and documentation effort: $2,000,000.

    - Risk Exposure (EMV): 0.50 * $2,000,000 = $1,000,000

#### 5. Estimation Risks

- Risk ID: E-1

- Risk Description: Underestimation of the time and computational resources needed to train complex models (e.g., 3D CNNs) on high-resolution image data.

  - Type: Threat

- Qualitative Analysis:

    - Probability: High

    - Impact: Medium (Budget overrun, missed deadlines).

    - Exposure: Medium

- Quantitative Analysis (EMV):

    - Probability: 60%

    - Impact: Additional cloud computing costs and developer overtime: $150,000.

    - Risk Exposure (EMV): 0.60 * $150,000 = $90,000

#### 6. Opportunities (Positive Risks)

- Risk ID: Opp-1

- Risk Description: A new, more efficient model architecture (e.g., a novel transformer) is published, which could make our system faster and more accurate.

- Type: Opportunity

- Qualitative Analysis:

    - Probability: Low

    - Impact: High (Market advantage, better patient outcomes).

    - Exposure: Low (due to low probability)

- Quantitative Analysis (EMV):

    - Probability: 20%

    - Impact: Faster time-to-market and increased sales, valued at a gain of $1,000,000.

    - Risk Exposure (EMV): 0.20 * -$1,000,000 = -$200,000 (Note the negative value for opportunity)

### Plan Risk Response

| Risk ID | Name of Risk | Risk Response Strategy | Response Plan (What shall we do?) |
| --- | --- | --- | --- |
| T-1 | Poor generalization to new scanners | Mitigate | Use extensive data augmentation during training. Partner with multiple hospitals to collect diverse data from the start. Implement "domain adaptation" techniques. |
| P-1 | Loss of key personnel | Mitigate | Implement pair programming and thorough documentation. Create a retention plan for key employees. Cross-train other team members. |
| O-1 | Data sharing difficulties | Transfer / Mitigate | Transfer: Hire a specialized legal firm to handle data-sharing agreements. Mitigate: Develop and use a sophisticated, on-premise data anonymization tool to assure partners. |
| R-1 | Changing regulations | Accept / Mitigate | Accept: Acknowledge this is part of the medical device landscape. Mitigate: Proactively engage with regulatory consultants early in the project to anticipate changes. |
| E-1 | Underestimation of resources | Mitigate | Build a 25% buffer into the compute budget. Run small-scale pilot tests early to better estimate full-scale training needs. |
| Opp-1 | New efficient model | Exploit | Dedicate a small, agile R&D team to monitor SOTA research and rapidly prototype promising new architectures. |

### Contingency Reserve Calculation (Quantitative)

Using the Expected Monetary Value (EMV) technique from your lecture:

Sum of Threats (EMV):

- T-1: $3,640,000

- P-1: $160,000

- O-1: $240,000

- R-1: $1,000,000

- E-1: $90,000

- Total Threats = $5,130,000

Sum of Opportunities (EMV):

- Opp-1: -$200,000

Contingency Reserve Needed:
Contingency Reserve = [Sum of Threats] – [Sum of Opportunities]
= $5,130,000 - $200,000
= $4,930,000

Conclusion: For this high-stakes medical project, the quantitative risk analysis suggests a contingency reserve of approximately $4.93 million is needed to cover the net expected impact of the identified risks.

### Software Risk Monitoring

- Tracking: A risk register (like the one above) will be maintained and reviewed bi-weekly.

- Monitoring Residual Risks: We will track the effectiveness of our mitigation for Risk T-1 by regularly testing the model on new, unseen data from partner hospitals.

- Identifying New Risks: Monthly brainstorming sessions will be held to identify new risks, such as the emergence of a competitor's product or newly discovered model biases.

- Evaluating Effectiveness: The overall risk management process will be reviewed at each major project milestone to ensure it is effectively protecting the project's objectives and patient safety.

## 🍎 Example: Buying a Bicycle Lock

You have a new bicycle worth £400, and you’re thinking about buying a lock to reduce the chance of it being stolen.

### Before buying the lock

- Chance of theft: 5%

- Cost if stolen: £400

Risk Exposure Before (REbefore)
= 5% × £400
= £20

### After buying the lock

The lock costs £10 and reduces theft chance to 2%.

Risk Exposure After (REafter)
= 2% × £400
= £8

### Risk Reduction Leverage (RRL)

Formula:
[

RRL=REbefore-REafterCost of risk reduction
]

Plug in the numbers:

[

RRL=£20-£8£10=£12£10=1.2
]

### 📌 Interpretation

- RRL = 1.2

- Because it’s greater than 1, buying the lock gives you more benefit than it costs.

- So it’s worth doing.