### Scenario 1: The Optimistic Project (Ahead of Schedule and Under Budget)

- Project Context: "FastTrack" Mobile App Development.

- Baseline Plan: Duration: 6 months, Total Budget (BAC): 600,000 PKR.

- Status Check: At the end of 3 months.

- Data:

  - Planned Value (PV) = (50% of BAC) = 300,000 PKR

  - Earned Value (EV) = (65% of BAC) = 390,000 PKR

  - Actual Cost (AC) = 280,000 PKR

- EVM Analysis & Interpretation:

- Calculate SV,CV,SPI,CPI

  - Schedule Variance (SV) = EV - PV = 390,000 - 300,000 = +90,000 PKR

    - Interpretation: Positive SV indicates the project is ahead of schedule. The team has delivered 90,000 PKR worth of work more than planned.

  - Cost Variance (CV) = EV - AC = 390,000 - 280,000 = +110,000 PKR

    - Interpretation: Positive CV indicates the project is under budget. The team has spent 110,000 PKR less than the value of the work they have created.

  - Schedule Performance Index (SPI) = EV / PV = 390,000 / 300,000 = 1.3

    - Interpretation: An SPI > 1.0 means the project is progressing at 130% of the planned rate. Highly efficient schedule performance.

  - Cost Performance Index (CPI) = EV / AC = 390,000 / 280,000 = 1.39

    - Interpretation: A CPI > 1.0 means the project is getting 1.39 PKR of value for every 1 PKR spent. Excellent cost efficiency.

### Scenario 2: The Troubled Project (Behind Schedule and Over Budget)

- Project Context: "DataSecure" Cloud Migration.

- Baseline Plan: Duration: 6 months, Total Budget (BAC): 600,000 PKR.

- Status Check: At the end of 4 months.

- Data:

  - Planned Value (PV) = (67% of BAC) = 402,000 PKR

  - Earned Value (EV) = (50% of BAC) = 300,000 PKR

  - Actual Cost (AC) = 450,000 PKR

- Calculate SV,CV,SPI,CPI

- EVM Analysis & Interpretation:

  - Schedule Variance (SV) = EV - PV = 300,000 - 402,000 = -102,000 PKR

    - Interpretation: Negative SV indicates the project is behind schedule. The team is behind by 102,000 PKR worth of work.

  - Cost Variance (CV) = EV - AC = 300,000 - 450,000 = -150,000 PKR

    - Interpretation: Negative CV indicates the project is over budget. The team has overspent by 150,000 PKR for the work accomplished.

  - Schedule Performance Index (SPI) = EV / PV = 300,000 / 402,000 = 0.75

    - Interpretation: An SPI of 0.75 means the project is only progressing at 75% of the planned rate.

  - Cost Performance Index (CPI) = EV / AC = 300,000 / 450,000 = 0.67

    - *Interpretation: A CPI of 0.67 means for every 1 PKR spent, only 0.67 PKR of value is earned. The project is 33% over budget (1 - 0.67 = 0.33).*

### Scenario 3: The "On Time but Over Budget" Project

- Project Context: "LegacyUpgrade" Server Hardware Replacement.

- Baseline Plan: Duration: 6 months, Total Budget (BAC): 600,000 PKR.

- Status Check: At the end of 5 months.

- Data:

  - Planned Value (PV) = (83% of BAC) = 498,000 PKR

  - Earned Value (EV) = (83% of BAC) = 498,000 PKR

  - Actual Cost (AC) = 570,000 PKR

- Calculate SV,CV,SPI,CPI

- EVM Analysis & Interpretation:

  - Schedule Variance (SV) = EV - PV = 498,000 - 498,000 = 0 PKR

    - Interpretation: SV of zero indicates the project is exactly on schedule.

  - Cost Variance (CV) = EV - AC = 498,000 - 570,000 = -72,000 PKR

    - Interpretation: Negative CV indicates the project is over budget.

  - Schedule Performance Index (SPI) = EV / PV = 498,000 / 498,000 = 1.0

    - Interpretation: An SPI of 1.0 confirms the project is on schedule.

  - Cost Performance Index (CPI) = EV / AC = 498,000 / 570,000 = 0.87

    - Interpretation: A CPI of 0.87 means the project is getting only 0.87 PKR of value for every 1 PKR spent. It is 13% over budget.

### Scenario 4: The "Behind Schedule but Under Budget" Project

- Project Context: "EcoWare" Sustainable Packaging Design.

- Baseline Plan: Duration: 6 months, Total Budget (BAC): 600,000 PKR.

- Status Check: At the end of 2 months.

- Data:

  - Planned Value (PV) = (33% of BAC) = 198,000 PKR

  - Earned Value (EV) = (25% of BAC) = 150,000 PKR

  - Actual Cost (AC) = 120,000 PKR

- Calculate SV,CV,SPI,CPI

- EVM Analysis & Interpretation:

  - Schedule Variance (SV) = EV - PV = 150,000 - 198,000 = -48,000 PKR

    - Interpretation: Negative SV indicates the project is behind schedule.

  - Cost Variance (CV) = EV - AC = 150,000 - 120,000 = +30,000 PKR

    - Interpretation: Positive CV indicates the project is under budget. The team is spending efficiently but not quickly enough.

  - Schedule Performance Index (SPI) = EV / PV = 150,000 / 198,000 = 0.76

    - Interpretation: An SPI of 0.76 means the project is only progressing at 76% of the planned rate.

  - Cost Performance Index (CPI) = EV / AC = 150,000 / 120,000 = 1.25

    - Interpretation: A CPI of 1.25 is excellent, meaning the project is getting 1.25 PKR of value for every 1 PKR spent. The issue is purely with schedule execution, not cost control.

These four scenarios illustrate how EVM provides a clear, objective, and integrated view of both cost and schedule performance, allowing a project manager to accurately diagnose a project's health and take corrective action.