## Real-Time Software Project Scenario

### Project Title: SmartBank Mobile Application

### Project Duration: March 1, 2025 – December 15, 2025 (9.5 months)

### Organization: DigitalEdge Solutions Pvt. Ltd.

### Client: National Trust Bank (NTB)

### Project Manager: Ms. Ayesha Khan

### Team Structure:

| Role | Name | Department |
| --- | --- | --- |
| Project Manager | Ayesha Khan | PMO |
| Technical Lead | Umar Siddiqui | Software Engineering |
| UI/UX Designer | Sara Ali | Design |
| Backend Developer | Bilal Ahmad | Development |
| Mobile App Developer | Rehan Ahmed | Development |
| QA Engineer | Fatima Noor | Quality Assurance |
| Database Administrator | Khalid Hussain | IT Operations |
| Client Liaison | Mr. Raza Rizvi | Business Analysis |

## 1️⃣    What is Management in this Project

Management Activities:

- Planning: Define project scope, modules, and deadlines.

- Organizing: Allocate team members to frontend, backend, and testing modules.

- Staffing: Hire a mobile app developer and QA engineer by March 10, 2025.

- Directing: Daily stand-ups and sprint reviews every two weeks.

- Monitoring: Weekly progress report to client and PM.

- Controlling: Risk log maintained to address timeline slippage.

- Innovating: Introduce AI-based fraud detection module.

- Representing: Liaise with NTB’s IT and Compliance Department.

## 2️⃣    What is the Project

A finite, goal-driven activity to:

- Develop a secure mobile banking app for NTB customers.

- Enable fund transfers, utility bill payments, and biometric login.

- Target completion within 9.5 months.

## 3️⃣   What is Software

The deliverable includes:

- Mobile app code (Android & iOS).

- Server-side procedures for transactions.

- Documentation (user manual, API guide).

- Test data and logs.

## 4️⃣     Project Management Phases

| Phase | Duration | Key Deliverables |
| --- | --- | --- |
| Initiation | Mar 1–Mar 15, 2025 | Feasibility Study, Project Charter |
| Planning | Mar 16–Apr 30, 2025 | WBS, Gantt Chart, Resource Allocation |
| Execution | May 1–Oct 15, 2025 | Development, Testing, Integration |
| Monitoring & Controlling | Continuous | Status Reports, Risk Updates |
| Closing | Oct 16–Dec 15, 2025 | User Acceptance, Final Delivery |

## 5️⃣    Differentiating Factors of the Software Project

- Intangible output (no physical product).

- Highly cognitive — requires logic, algorithms, and teamwork.

- Uncertain scope — bank may request new compliance features.

- Heavy documentation and coordination needed.

- Quality difficult to quantify — measured via user satisfaction and bug count.

## 6️⃣   Comparing Project vs Operations

| Aspect | Project | Operations |
| --- | --- | --- |
| Definition | Temporary endeavor | Ongoing activity |
| Example | Develop SmartBank app | Daily transaction processing |
| Duration | 9.5 months | Continuous |
| Objective | Deliver mobile app | Maintain banking services |

## 7️⃣   Project Management Framework (PMI-based)

| Knowledge Area | Example in SmartBank Project |
| --- | --- |
| Integration | Combine modules from frontend, backend, and API gateway |
| Scope | Define 8 modules: Login, Dashboard, Payments, etc. |
| Time | Gantt chart with milestones |
| Cost | Budget = USD 250,000 |
| Quality | Testing via 4 QA cycles |
| HR | 8-member cross-functional team |
| Communications | Weekly Zoom updates with NTB |
| Risk | Server downtime, regulatory changes |
| Procurement | Buy third-party API licenses |
| Stakeholder | NTB board, end-users, IT team |

## 8️⃣    Factors Used to Differentiate This Project

| Level | Factor | Description |
| --- | --- | --- |
| Organization | Business Domain | Banking / Finance |
|  | Number of Instances | 1 app for 3M customers |
|  | Innovation Level | AI-based fraud detection |
| Project | Size | Medium (~50K LOC) |
|  | Architecture | Microservice architecture |
|  | Team Distribution | Single location, hybrid work |
|  | Age of System | Greenfield (new) |
|  | Criticality | High — impacts financial data |
|  | Governance | Reports to NTB’s CIO |

## 9️⃣   Type of Software Project

Type: Bespoke Software

- Custom-built for NTB’s needs.

- Includes training and post-deployment maintenance contract.

Other linked components:

- Process Reengineering: Integrating legacy ATM and web systems.

- System Integration: Connecting NTB’s existing Oracle DB and transaction APIs.

- Installation & Training: On-site workshops for NTB staff (Dec 2025).

## 🔟 Project Timeline Snapshot

| Milestone | Date | Deliverable |
| --- | --- | --- |
| Kickoff | Mar 1, 2025 | Project Charter |
| Design Approval | Apr 15, 2025 | UI Mockups |
| Prototype | Jun 15, 2025 | Basic working app |
| Beta Testing | Sep 15, 2025 | User feedback |
| Final Release | Dec 1, 2025 | Full deployment |
| Closure | Dec 15, 2025 | Handover report |

Summary

This SmartBank Mobile Application project integrates every aspect from your lecture:

- Shows management activities

- Illustrates project lifecycle

- Follows PMI knowledge areas

- Demonstrates differentiating software factors

- Represents a real, dated case study suitable for classroom discussion or report writing.