Question 1 – Earned Value Management Analysis

Given Data

Budget at Completion (BAC) = $800,000
Earned Value (EV) = $350,000
Planned Value (PV) = $400,000
Actual Cost (AC) = $420,000

Expected deterioration:

- CPI deterioration = 20%

- SPI deterioration = 25%

Originally planned project duration = 12 months

1. Current Cost Performance Index (CPI)

Formula:
CPI = EV / AC

Calculation:
CPI = 350,000 / 420,000
CPI = 0.83

Interpretation:
The CPI is less than 1, which means the project is over budget. For every $1 spent, only $0.83 worth of work is being earned.

2. Current Schedule Performance Index (SPI)

Formula:
SPI = EV / PV

Calculation:
SPI = 350,000 / 400,000
SPI = 0.875

Interpretation:
The SPI is less than 1, which indicates the project is behind schedule. Only 87.5% of the planned work has been completed.

3. Adjusted CPI and Adjusted SPI (After Deterioration)

Adjusted CPI

Formula:
Adjusted CPI = CPI × (1 − Deterioration %)

Calculation:
Adjusted CPI = 0.83 × (1 − 0.20)
Adjusted CPI = 0.83 × 0.80
Adjusted CPI = 0.66

Adjusted SPI

Formula:
Adjusted SPI = SPI × (1 − Deterioration %)

Calculation:
Adjusted SPI = 0.875 × (1 − 0.25)
Adjusted SPI = 0.875 × 0.75
Adjusted SPI = 0.66

4. Revised Estimate at Completion (EAC)

Formula:
EAC = AC + (BAC − EV) / Adjusted CPI

Calculation:
EAC = 420,000 + (800,000 − 350,000) / 0.66
EAC = 420,000 + 450,000 / 0.66
EAC = 420,000 + 681,818
EAC ≈ $1,101,818

Interpretation:
Due to declining cost performance, the project is expected to exceed the original budget by approximately $301,818.

5. Revised Expected Project Duration

Formula:
Revised Duration = Original Duration / Adjusted SPI

Calculation:
Revised Duration = 12 / 0.66
Revised Duration ≈ 18.18 months ≅ 18 Months and 15 days

Final Interpretation (Cost and Schedule Impact)

- The CPI of 0.83 shows that the project is over budget, as more money is being spent than the value of work completed.

- The SPI of 0.875 indicates that the project is behind schedule, since less work has been completed than planned.

- Due to a shortage of skilled staff, project performance is expected to worsen, reducing both CPI and SPI to 0.66.

- The revised Estimate at Completion (EAC) is approximately $1.1 million, which means the project will exceed the original budget by about $300,000.

- The revised project duration is approximately 18 months and 15 days, compared to the planned 12 months, showing a delay of over 6 months.

- Overall, the project is facing serious cost overruns and schedule delays, and corrective actions are needed to control further losses.