SIR SYED UNIVERSITY OF ENGINEERING & TECHNOLOGY

COMPUTER SCIENCE & INFORMATION TECHNOLOGY DEPARTMENT

Fall  2025

IT Project Management (IT-316)

Assignment # 3

Semester: IV									Batch: 2022F

Announced Date: 12 January 2026			     	     	        Due Date: 16th January 2026

Total Marks:3									Marks Obtained:

Instructor Name: Umair Khan

Name: Muhammad Faisal

Roll#: 2022F-BCS-152

Section: E

| CLO # | Course Learning Outcomes (CLOs) | PLO Mapping | Bloom’s Taxonomy |
| --- | --- | --- | --- |
| CLO 3 | Apply project management concepts to explain a given scenario. | PLO-3 (Problem Analysis) | C3 (Applying) |

Q1. An IT infrastructure upgrade project is at the 50% completion mark. The following data is recorded:

- Budget at Completion (BAC): $800,000

- Earned Value (EV): $350,000

- Planned Value (PV): $400,000

- Actual Cost (AC): $420,000

Management predicts project performance will worsen due to shortages in skilled personnel:

- Expected CPI deterioration: 20%

- Expected SPI deterioration: 25%

Using the data provided above:

- Compute the current CPI.

- Compute the current SPI.

- Calculate the Adjusted CPI and Adjusted SPI using the deterioration percentages.

- Using the adjusted CPI, compute the revised Estimate at Completion (EAC) with the formula:

EAC=AC+BACEVAdjusted CPI

- The original planned duration for the project was 12 months. Calculate the revised expected project duration using:

Revised Duration=12Adjusted SPI

Provide full calculations and a short interpretation of the impact on cost and schedule.