Software Project Management

Assignment #3

Q1. An IT infrastructure upgrade project is at the 50% completion mark. The following data is recorded:

- Budget at Completion (BAC): $800,000

- Earned Value (EV): $350,000

- Planned Value (PV): $400,000

- Actual Cost (AC): $420,000

Management predicts project performance will worsen due to shortages in skilled personnel:

- Expected CPI deterioration: 20%

- Expected SPI deterioration: 25%

Using the data provided above:

- Compute the current CPI.

- Compute the current SPI.

- Calculate the Adjusted CPI and Adjusted SPI using the deterioration percentages.

- Using the adjusted CPI, compute the revised Estimate at Completion (EAC) with the formula:

𝐸𝐴𝐶=𝐴𝐶+(𝐵𝐴𝐶−𝐸𝑉)Adjusted CPI

- The original planned duration for the project was 12 months. Calculate the revised expected project duration using:

Revised Duration=12/Adjusted SPI

Provide full calculations and a short interpretation of the impact on cost and schedule.

Solution

## Given Data

- BAC = $800,000

- EV = $350,000

- PV = $400,000

- AC = $420,000

Expected deterioration:

- CPI deterioration = 20%

- SPI deterioration = 25%

## 1. Current Cost Performance Index (CPI)

Formula:

CPI=EV/ AC

Calculation:

CPI=350,000/420,000

Result:

CPI≈0.83

## 2. Current Schedule Performance Index (SPI)

Formula:

SPI=EV/PV

Calculation:

SPI=350,000/400,000

Result:

SPI=0.875

## 3. Adjusted CPI and Adjusted SPI

### Adjusted CPI (20% deterioration)

Adjusted CPI=CPI×(1−0.20)

=0.833×0.80=0.666

Adjusted CPI=0.67

### Adjusted SPI (25% deterioration)

Adjusted SPI=SPI×(1−0.25)

=0.875×0.75=0.656

Adjusted SPI=0.66

## 4. Revised Estimate at Completion (EAC)

Formula (as given in the question):

EAC=AC+[(BAC−EV)/Adjusted CPI ]

Calculation:

BAC−EV=800,000−350,000=450,000

EAC=420,000+[450,000/0.666]

​EAC=420,000+675,675

EAC=$1,095,675

## 5. Revised Expected Project Duration

Original Duration = 12 months

Formula:

Revised Duration=12/Adjusted SPI

Calculation:

Revised Duration=12/0.656=18.29

Revised Duration=18.3 months​

## Interpretation (Cost & Schedule Impact)

- The current CPI (0.83) shows the project is already over budget, earning only $0.83 per $1 spent.

- The current SPI (0.88) indicates the project is behind schedule.

- With predicted performance deterioration, efficiency worsens significantly:

  - Adjusted CPI = 0.67 → severe cost inefficiency

  - Adjusted SPI = 0.66 → major schedule slippage

- The revised EAC (~$1.10M) exceeds the original budget by almost $296,000, indicating a substantial cost overrun.

- The project duration increases from 12 months to ~18 months, reflecting serious delays due to skilled labor shortages.

Overall: If corrective actions are not taken, the project will finish much later and far more expensive than originally planned.