# Case Study: Applying COCOMO and Function Point Analysis in the Health Sector

## Background

A healthcare organization is building a comprehensive Electronic Health Record (EHR) system to improve patient data management, appointment scheduling, billing, medical device integration, and reporting. Accurate estimation is critical to ensure on-time delivery within budget. The organization uses COCOMO for technical effort estimation and Function Point Analysis (FPA) for user-centric functionality assessment.

## System Requirements

The EHR system includes:
1. Patient Management Module: Registration, demographics, and history tracking.
2. Appointment Scheduling: Calendar integration and reminders.
3. Billing System: Insurance claims and patient billing.
4. Medical Device Integration: Real-time data collection (e.g., ECG, heart rate).
5. Reporting Module: Customizable reports for patients and administrators.

## Application of COCOMO

COCOMO classifies projects as Organic, Semi-detached, or Embedded. This EHR system is classified as Semi-detached due to its moderate complexity and integration requirements.

### Effort Calculation

The effort equation is:
Effort (PM) = a × (Size)^b × ∏ EMs

• Semi-detached parameters: a = 3.0, b = 1.12
• Size: 150,000 Delivered Source Instructions (DSI)

• Effort Multipliers (EMs):
  - Personnel experience = 1.15
  - Complexity = 1.30
  - Required reliability = 1.25
  - Platform constraints = 1.20
  - Tools used = 0.90

Substituting values:

Effort (PM) = 3.0 × (150)^1.12 × (1.15 × 1.30 × 1.25 × 1.20 × 0.90)

### COCOMO Effort Estimate

Productivity

Effort (PM) ≈ 1072.53 Person-Months

## Application of Function Point Analysis (FPA)

FPA measures software size based on functionality and environmental factors, using Unadjusted Function Points (UFP) and a Value Adjustment Factor (VAF).

### Step 1: Identify and Categorize Functions

| Function Type | Count | Complexity | Weight |
| --- | --- | --- | --- |
| External Inputs (EI) | 50 | Medium | 4 |
| External Outputs (EO) | 30 | High | 7 |
| External Inquiries (EQ) | 20 | Low | 3 |
| Internal Logical Files (ILF)¦ | 40 | Medium | 10 |
| External Interface Files (EIF)¦ | 15 | High | 7 |

Unadjusted Function Points (UFP) = 975

### Step 2: Value Adjustment Factor (VAF)

The VAF adjusts the UFP based on 14 General System Characteristics (GSCs). Each characteristic is rated from 0 (no influence) to 5 (strong influence):

| GSC | Rating |
| --- | --- |
| Data Communications | 4 |
| Distributed Processing | 4 |
| Performance | 5 |
| Heavily Used Config. | 3 |
| Transaction Rate | 5 |
| Online Data Entry | 5 |
| End-User Efficiency | 4 |
| Online Update | 5 |
| Complex Processing | 4 |
| Reusability | 4 |
| Installation Ease | 2 |
| Operational Ease | 3 |
| Multiple Sites | 4 |
| Facilitate Change | 3 |

Total Influence Score = 54

VAF = 0.65 + (0.01 × Total Influence Score) = 1.19

### Step 3: Adjusted Function Points (AFP)

AFP = UFP × VAF = 975 × 1.19 = 1160.25

### Step 4: Effort Estimation

Effort (PM) = AFP / Productivity = 1160.25 / 10 = 116.03 Person-Months

## Comparison of Estimates

| Method | Original Effort (PM) | Revised Effort (PM | Cost ($) |
| --- | --- | --- | --- |
| COCOMO | 1072.53 | N/A | $10.73M |
| FPA | 107.25 | 116.03 | $1.16M |

## Analysis and Recommendations

1. Discrepancy in Estimates:
   - COCOMO focuses on technical challenges, leading to higher effort estimates.
   - FPA provides a user-centric view, resulting in lower estimates.

2. Refinement of FPA:
   - The revised VAF reflects the EHR system's real-world complexity and characteristics.

3. Balanced Planning:
   - Use COCOMO for technical resource allocation and risk management.
   - Use FPA for functional scoping and cost estimation.

4. Risk Mitigation:
   - Allocate contingency based on the higher COCOMO estimates for unforeseen complexities.

5. Periodic Reassessment:
   - Reevaluate both estimates during development to ensure alignment with evolving requirements.

## Conclusion

COCOMO and FPA offer complementary insights into project estimation for the EHR system. While COCOMO highlights technical complexity, FPA focuses on user functionality. By combining these methods, the healthcare organization can achieve accurate planning and resource allocation, ensuring successful project execution.