## Identify Functional Components
Imagine we are developing an online banking system that allows customers to:
|  | Type | Complexity
1 | View Account Balance | External Input (EI) | Low
2 | Fund Transfer | External Input (EI) | High
3 | Pay Bills | External Input (EI) | High
4 | View Transaction History | External Input (EI) | Low
5 | Change Account Settings | External Input (EI) | Medium
6 | Account Details Report | External Output (EO) | Medium
7 | Transfer Confirmation Message | External Output (EO) | Low
8 | Transaction History Query | External Query (EQ) | Medium

## GSC Implementation
GSC # | GSC Name | Cash Withdrawal | Amount Transfer | Bank Statement | Pay Bill | Pay Fees | Biometric | SMS | Email | Car Finance | Home Loan | Fine
1 | Data Communications | 4 | 5 | 3 | 4 | 3 | 2 | 3 | 2 | 4 | 4 | 3 | 0: No influence
2 | Distributed Data Processing | 4 | 4 | 3 | 4 | 3 | 2 | 2 | 2 | 4 | 4 | 3 | 1: Incidental influence
3 | Performance | 5 | 5 | 4 | 4 | 3 | 2 | 3 | 2 | 4 | 4 | 3 | 2: Moderate influence
4 | Heavily Used Configuration | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 2 | 4 | 4 | 3 | 3: Average influence
5 | Transaction Complexity | 4 | 5 | 4 | 5 | 4 | 2 | 2 | 2 | 5 | 5 | 3 | 4: Significant influence
6 | Conversion and Installation | 2 | 3 | 2 | 3 | 3 | 3 | 2 | 2 | 4 | 4 | 3 | 5: Strong influence
7 | Application Design | 4 | 4 | 3 | 4 | 3 | 3 | 3 | 3 | 4 | 4 | 3
8 | System Interface | 4 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 5 | 5 | 4
9 | Internal Processing | 4 | 5 | 4 | 5 | 4 | 3 | 3 | 3 | 5 | 5 | 4
10 | Code Volume | 4 | 5 | 3 | 5 | 4 | 3 | 2 | 2 | 5 | 5 | 3
11 | Complexity of User Interface | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 5 | 5 | 3
12 | Reusability | 4 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | 4 | 4 | 3
13 | Installability | 3 | 4 | 3 | 4 | 4 | 3 | 2 | 2 | 4 | 4 | 3
14 | Operational Ease | 4 | 5 | 4 | 5 | 4 | 3 | 3 | 3 | 5 | 5 | 4
15 | Multi-User Capability | 5 | 5 | 4 | 5 | 4 | 3 | 3 | 3 | 5 | 5 | 4
| GSCs | 59 | 68 | 52 | 64 | 54 | 42 | 40 | 37 | 67 | 67 | 49
| Sum of GSCs | 599

## General System Characteristic
GSC # | General System Characteristic | Rating (0-5) | Description
1 | Data Communications | 4 | Degree to which the system relies on communication protocols.
2 | Distributed Data Processing | 3 | Whether data processing is distributed across multiple locations.
3 | Performance | 5 | Impact of performance requirements on the system’s design.
4 | Heavily Used Configuration | 3 | Extent to which the system will have a high usage volume.
5 | Transaction Complexity | 4 | Complexity of the transactions or business logic.
6 | Conversion and Installation | 2 | Complexity of data conversion and system installation.
7 | Application Design | 3 | Impact of the design on system complexity.
8 | System Interface | 5 | Degree of complexity in interfacing with external systems.
9 | Internal Processing | 4 | Complexity of internal system processing, such as logic.
10 | Code Volume | 4 | Extent of coding effort required for the system.
11 | Complexity of User Interface | 2 | Complexity of the user interface and user interactions.
12 | Reusability | 1 | How much of the system is reusable for future projects.
13 | Installability | 2 | Complexity of installing the system into the operating environment.
14 | Operational Ease | 3 | Complexity involved in system operation and maintenance.
15 | Multi-User Capability | 4 | Complexity of managing multiple users.

## Calculation
Weighting Factor
Number of external inputs (I) | 30 | 4 | 120
Number of external outputs (O) | 60 | 5 | 300
Number of external inquiries ('E) | 23 | 4 | 92
Number of files (F) | 8 | 10 | 80
Number of external interfaces (N) | 2 | 7 | 14
606
FP = UPF * VAP
FP= 606 *[ 0.65 +0.01 * [∑GSC)
GSC = 4*0 + 4*3 + 6*4
GSC = 36
FP= 606 *[ 0.65 +0.01 * [∑GSC]]
FP= 606 *[ 0.65 +0.01 * 36] |  |  | 612.06
UPF = Unadjusted function points
VAF= Value adjustment factor